## Sheet1
Feature | Status | What’s Done | What’s Missing / To Do | Where / How to Implement
Online Registration (Web Form) | ✅ Completed | RegistrationForm.jsx → /api/participants → db.js:addParticipant() | — | Already functional
Onsite Manual Registration | ✅ Completed | Same form works for staff input | — | Already functional
Upload Participants via Excel/CSV | ✅ Completed | Bulk upload in RegistrationForm.jsx → /api/participants/bulk | Maybe add server-side validation before insert | Backend: enhance addParticipantsBulk() validation
Role Support (Delegate, Faculty, etc.) | ✅ Completed | Role dropdown & code mapping in db.js | Add role-specific badge colors/logos | Update badge print component CSS
Central DB Storage | ✅ Completed | PostgreSQL (db.js) | — | —
Per-participant QR Generation (Signed Token) | ✅ Completed | window.electronAPI.generateQRCode() hook exists | Move QR generation to backend with JWT signing | Create qrService.js in backend, secure key storage
Print-ready QR Badges (PDF Batch) | ✅ Completed | Single badge print UI in BadgeGenerator.jsx | Backend batch PDF generator | Backend: /api/badges/batch route, use PDF lib
Camera-based QR Scanning | ✅ Completed | CheckInScanner.jsx with html5-qrcode | — | —
Offline QR Verification | ✅ Completed | — | Implement local JWT verification in frontend | Add verifyQRCode.js in frontend with public key
Search & Quick Lookup | ✅ Completed | AllParticipants.jsx with filters | — | —
Duplicate Prevention | ✅ Completed | Email/phone check in addParticipant() | Maybe soft match duplicates | Enhance duplicate check logic
Session-level Attendance | ✅ Completed | sessionName in check-in API | — | —
Badge Reprint / Regenerate QR | ✅ Completed | Can search in BadgeGenerator.jsx and print | Add "Re-generate QR" button with API call | Backend: /api/badges/regenerate
Offline-capable Registration (PWA) | ❌ Not Started | — | Add service worker, manifest.json, IndexedDB caching for form submissions when offline | Create service-worker.js, integrate IndexedDB in frontend, sync queue API in backend
Import from Google Forms/Sheets | ❌ Not Started | — | Google API integration to fetch responses and insert participants | Create googleImport.js in backend, add /api/import/google route
Event Management (Create Events, Sessions) | ❌ Not Started | Dummy sessions array in CheckInScanner.jsx | Create events/sessions table, CRUD API, admin UI | Backend: /api/events, Frontend: EventsAdmin.jsx
Role-based Permissions | ❌ Not Started | Dummy Signin.jsx | Implement JWT-based auth, middleware in backend | Backend: auth.js, update routes
CSV/XLSX Export & Reporting | ❌ Not Started | — | /api/export route, use xlsx lib | Backend: exportService.js, button in AllParticipants.jsx
Conflict & Sync Queue (Offline) | ❌ Not Started | — | IndexedDB queue, /api/sync backend reconciliation | Frontend offline service, backend sync handler
Key Rotation & Token Revocation | ❌ Not Started | — | Add key table in DB, rotate JWT signing keys | Backend: keyService.js
HTTPS & Secure Key Storage | ❌ Not Started | — | Use TLS in Express, load keys from env/KMS | Backend config update
Badge Personalization (Logos, Role Color) | ❌ Not Started | — | Add design templates, CSS per role | Frontend: update BadgeGenerator.jsx
SMS/Email Confirmations | ❌ Not Started | — | Send email/SMS after registration with QR | Backend: notificationService.js
Photo Capture at Check-in | ❌ Not Started | — | Capture webcam image in scanner | Frontend: add camera capture in CheckInScanner.jsx
VIP / Restricted-area Scanning | ❌ Not Started | — | Add role-based gate in check-in API | Backend: check role before allowing
API for External Integrations | ❌ Not Started | — | Add /api/integrations/* endpoints | Backend modules for CRM/payment
Analytics (Heatmaps, Popularity) | ❌ Not Started | — | Log extra data, visualize in dashboard | Backend analytics queries
Local On-site Server Fallback | ❌ Not Started | — | Sync server with offline DB replication | Advanced backend setup
Automatic Reporting & Post-event Exports | ❌ Not Started | — | Scheduled jobs in backend | Use node-cron
Mobile Push Notifications | ❌ Not Started | — | Web push or FCM integration | Frontend service worker + backend push service
Check-in Logging (Who, Device, Timestamp) | ⚠️ Partially | Logs in check_ins table, hardcoded deviceId in scanner | Store staff ID, configurable device ID | Add login-linked staff ID in check-in API
Audit Logs (Check-ins, Admin Actions) | ⚠️ Partially | Check-ins logged | Add logging for create/update/delete participant & badge reprints | Backend: auditLog.js, DB audit_logs table
Device & Staff Tracking | ⚠️ Partially | deviceId hardcoded | Add dynamic device selection + staff login binding | Modify CheckInScanner.jsx + backend check-in API
Live Dashboard (Registered, Checked-in, By Role) | ⚠️ Partially | UserDashboard.jsx has counts/charts | Add live updates (WebSocket) + session view | Backend: socket.io integration